## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Test Engineer | 2025-10-05 | False positive for "No Helmet" violation when a pedestrian with a hat is detected near a traffic light. | Sprint 2 | Data Scientist | Logical | Refined YOLOv8 training dataset with more varied "hat" examples; adjusted confidence threshold. | 2025-10-18 | Closed | Resolution verified in testing on 2025-10-19.
2 | Intern | 2025-10-15 | Flask server crashes after processing a video file larger than 50MB. | Sprint 3 | Backend Dev | Maintainability | Increased max upload file size limit in Flask configuration (MAX_CONTENT_LENGTH). | 2025-10-23 | Closed | Tested with 100MB video, successful processing.
3 | Project Lead | 2025-10-22 | Violation count display on the web dashboard doesn't update in real-time; requires manual page refresh. | Sprint 4 | Frontend Dev | User Interface | Implemented AJAX calls to periodically fetch and update violation data without a full page reload. | 2025-11-01 | Closed | Smooth real-time update achieved; refresh every 5 seconds.
4 | Intern | 2025-10-29 | Code contains hardcoded API key for the external map service in the app.py file. | Sprint 5 | Backend Dev | Standards | Moved API key to a .env file and loaded it using Python's os module for security. | 2025-11-06 | Closed | Environment variable loading tested successfully.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others